## Sheet1
id | Headline | Submit_Date | Family | Product | Area | Subarea | AreaPath | Priority | Impact | Severity | State | Reason | Work_Process | Version_Number | Build | Owner.Email | Owner Name | Submitter.Email | Fixed_Ver | Fixed_Build | Doc_Impact | Defect_Type | Found_By | Detected_In | Triage_Status | Triage_By.Email | Triage By name | Triage_Date | ReleaseMediaImpact | Customer_Name | Actual_Effort | Calculation_Diff_Reason | Client_OS | Client_Config | Server_OS | Server_Config | Compatibility_Impact | Compatibility_Imp_Status | Engine_Baseline_Impact | Estimate | Fixed_By.Email | Fixed By Name | Notes | Portability_Impact | Release_Note | Resolution | Resolution_Description | RootCauseSubType | RootCause | Root cause_Comment | Salesforce_Case_ID | TestCase_Impact_Status | Workaround | Repro Steps | Tags | History
CQ00519191 | Re-Execute Calculator and Transfer blocks / options | 2013-09-03 13:54 | Chemical Supply Chain | Aspen SCM | Overall Application |  | AspenTech Sandbox | 5-Low | 4-Minor | S4-Minor | Closed | In Progress | No Activity | V8.4 |  | Marvin.Dai@aspentech.com | Eric Zhao | Jay.Thalal@aspentech.com | V8.7 | SCF V8.7 Media41 | 0 | Does Not Work As Designed | Customer | Beta Testing | Completed | amanda.mao@aspentech.com | Eric Zhao | 2014-01-24 13:27 |  | WESTLAKE GROUP-HOUSTON, TX | 8 |  |  |  | Multiple - See Configuration |  | 0 | Open |  | 16 | Marvin.Dai@aspentech.com | Eric Zhao | ==== State: Closed by: Cathy_Wu on 01 July 2014 21:55:51 ==== Verified by Yichen_Wu. ==== State: PendingVerification by: Yichen_Wu on 20 June 2014 11:21:24 ==== Verified on Windows 8 against v8.7 32bit SCM/CAPS Media 48. ==== State: Implemented by: Marvin_Dai on 22 April 2014 04:46:54 ==== The progress bar can appear in both windows and update simultaneously in both windows now. ==== State: Approved by: Amanda_Mao on 24 January 2014 13:26:49 ==== Email triage: agree to approve for V8.7 as part of the CQ reduction plan ==== State: Deferred by: Amanda_Mao on 11 September 2013 10:05:26 ==== Triage team: agree to defer to future release ==== State: Submitted by: Jay_Thalal on 03 September 2013 13:57:29 ==== Reported on V8.4. |  | 0 | Fixed | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open | N/A | ==== State: Submitted by: Scopus_Incident on 03 September 2013 13:54:10 ==== Defect created by Support from Incident: 1333264 By: Jay_Thalal Customer: Westlake Chemical Corporation at Site: WESTLAKE GROUP-HOUSTON, TX Customer Contact: Captain, Jennifer at 281 584 5456 Incidents Date and Time Stamps: Created: 03-Sep-2013 01:52 SLA: 01-Oct-2013 01:52 Client: 01-Oct-2013 01:52 Incidents Area Word(s): Overall Application ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1333264 ======================================================= No attachments were associated with the Scopus Incident. ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: Aspen Technology, Inc. Site: WESTLAKE GROUP-HOUSTON, TX Caller: Captain, Jennifer Incident Product: Aspen SCM Reproduction Steps: 1. I opened planning boards in two windows (open PB in Aspen SCM and then go to the Navigation Pane, right click on PB and click on Open in New Window option). 2. I ran the Schedule Generation from Run Action menu on one screen. 3. The progress meter appeared in only one window. 4. I tried to make some changes in the other window. The application did not allow me to. The hourglass (or the ring in Windows 7) started to appear. Eventually the progress meter also appeared in the other window. Now, the progress meter that appeared initially in the first window stopped updating. The new progress meter updated and completed. 5. The old progress meter did not update and did not close. It stayed at the old level. Due to the recent change in progress meter locking out the screen - It did not allow me to click anywhere on this window. But there is an X mark at the top of the progress meter, which when closed, allowed me to continue my activities in that window. 6. This seems to be a bug. I would have expected the Progress meter to: a. Appear in both windows. b. Update simultaneously in both windows. c. Close in both windows once processing completes. 7. But I would not consider this as a showstopper, since screen locked out correctly when processing and everything was normal after progress meter was closed in both screens (at least thats my view). Screenshots are in attachment
CQ00521505 | Ellipsoidal and Hemisphere head -- not yet supported for Vertical! %$!@#%^&*(){}¦\';,.?/`~ | 2013-09-20 10:32 | Aspen Engineering Suite | Aspen HYSYS | Unit Operations | Vessels - Separator | AspenTech Sandbox | To be set at Review | 4-Minor | S4-Minor | Closed | In Progress | No Activity | V8.3 |  | Ricardo.Gutfraind@aspentech.com | Gutfraind, Ricardo | Gerardo.Munoz@aspentech.com |  |  | 0 | Question | Customer | Post Release | Required |  |  |  |  | WORLEYPARSONS-ANCHORAGE, AK |  |  |  |  | Multiple - See Configuration |  | 0 | Open |  |  |  |  | ==== State: Assigned by: Gerardo_Munoz on 23 September 2013 09:32:45 ==== Thank you Ricardo. Please close this CQ. I will talk to the customer and if interested, ill create a new CQ with an enhancement request. ==== State: Assigned by: Ricardo_Gutfraind on 22 September 2013 10:03:28 ==== No it is not in the roadmap at this moment. you can submit an enhancement request. | 0 | 0 | Answered | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open | N/A | ==== State: Submitted by: Scopus_Incident on 20 September 2013 10:31:58 ==== Defect created by Support from Incident: 1337517 By: Gerardo_Munoz Customer: WorleyParsons at Site: WORLEYPARSONS-ANCHORAGE, AK Customer Contact: Munoz, Gerardo at +525536007116 Incidents Date and Time Stamps: Created: 20-Sep-2013 10:29 SLA: 18-Oct-2013 10:29 Client: 18-Oct-2013 10:29 Incidents Area Word(s): Unit Operations,Vessels,Separator ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1337517 ======================================================= No attachments were associated with the Scopus Incident. ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: Aspen Technology, Inc. Site: WORLEYPARSONS-ANCHORAGE, AK Caller: Munoz, Gerardo Incident Product: Aspen HYSYS When you try to rate a vertical vessel with ellipsoidal or hemispherical head you get the following message: "Ellipsoidal and Hemisphere head -- not yet supported for Vertical!" Do you know if there is a time frame for this to be supported? Thanks in advance
CQ00522580 | Version 8.4 beta mbo bug. New version requires a trend limit for both VOLUME and WEIGHT | 2013-09-30 23:58 | Aspen PIMS Family | Aspen Refinery Multi-Blend Optimizer | Event Operation |  | AspenTech Sandbox | 3-High | 3-Important | S3-Medium | Closed | In Progress | No Activity | V8.4 |  | Boris.Zamsky@aspentech.com | Eric Zhao | KaYee.Kuah@aspentech.com | V8.4 | 12.4.19 | 0 | Does Not Work As Designed | Customer | Beta Testing | Completed | Donna.Fontenot@aspentech.com | Fontenot, Donna | 2013-10-02 12:08 |  | EXXONMOBIL-FAIRFAX, VA | 4 |  |  |  | Multiple - See Configuration |  | 0 | Open |  | 16 | Boris.Zamsky@aspentech.com | Eric Zhao | ==== State: Closed by: Shuanglai_Zhang on 12 October 2013 01:21:30 ==== Tested on MBO V8.4 Build B071/7.4.19.0 32 bit Custom installation on Windows 8 64-bit System. The model can be opened and optimized without any error. ==== State: Implemented by: Narasimha_Sontinenti on 08 October 2013 15:21:49 ==== Code Review : Pass ==== State: Approved by: KaYee_Kuah on 07 October 2013 17:43:29 ==== Hi R&D team, Is it accurate to communicate to customer that this will fixed in V8.5? If so, can you please kindly comment that what will be fixed? Thank you. Regards, Ka Yee Kuah |  | 0 | Fixed | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: | Error | Coding | Wrong string comparison |  | Open | Poor | ==== State: Submitted by: Scopus_Incident on 30 September 2013 23:58:01 ==== Defect created by Support from Incident: 1340011 By: KaYee_Kuah Customer: ExxonMobil at Site: EXXONMOBIL-FAIRFAX, VA Customer Contact: Evans, Joe at 1-703-846-5326 Incidents Date and Time Stamps: Created: 30-Sep-2013 09:21 SLA: 15-Oct-2013 09:00 Client: 15-Oct-2013 09:00 Incidents Area Word(s): Event Screen,Trend Chart ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1340011 ======================================================= ID: 3834770Filename: demo84_nowgttrends.zip Size: 1747033 ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: ExxonMobil Site: EXXONMOBIL-FAIRFAX, VA Caller: Evans, Joe Incident Product: Aspen Refinery Multi-Blend Optimizer Hi R&D team, This is a request from customer doing V8.4 beta testing. Currently there is a workaround but it is no suitable for long term use. Customer has the below comments: "In the version 8.4 MBO beta, I get error messages for tanks WGT being below their minimum values (the minimum values coming from the TANKS table) when I first open the model during simulation, even though a valid VOL trend limit with adjusted lower limits exist. I was able to work around for now by adding addition trend charts for the WGT and setting those limits manually to match those on the VOL trend limits, this is unacceptable for long term use. In prior versions of MBO, either the WGT equation was never explicitly added to the model and hence the bounds were never important, or the tool automatically translated any VOL trends into appropriate WGT trends. In the attached model, logon as admin, single day campaign. When you open the model it will complain about simulator errors on WGT in four tanks. If you replace the table TREND_SCREENS with the TREND_SCREENS_WITH_WGT then it works fine.. Demo Refinery Case : PLANNING Date : 09/30/13 Time : 18:06:24 SIMULATION ERROR LOG 0 , 4 N - Note, W - Warning, E - Error, P - Program Error W1051 Occurrence: 0001 Tank T531: Initial WGT = 0.000658 is below minimum = 3293 W1051 Occurrence: 0001 Tank T355: Initial WGT = 0.00074350002 is below minimum = 2401.3501 W1051 Occurrence: 0001 Tank T368: Initial WGT = 0.00069500005 is below minimum = 1775.67 W1051 Occurrence: 0001 Tank T470: Initial WGT = 0.00074500003 is below minimum = 3256.51" Please see attched model. Thank you. Regards, Ka Yee Kuah
CQ00523042 | A novel is a relatively long work of narrative fiction, typically written in prose and published as a book. The present English word for a long work of prose fiction derives from the Italian: novella for "new", "news", or "short story of something new", i can do it | 2013-10-08 05:03 | Aspen Engineering Suite | Aspen HYSYS | Unassigned | Acid Gas Cleaning | AspenTech Sandbox | 3-High | 2-Urgent | S2-Major | Closed | In Progress | No Activity | V8.3 |  | Pradeep.Polisetty@aspentech.com | Pradeep Polisetty | Gopal.Paul@aspentech.com |  |  | 0 | Does Not Work As Designed | Customer | Post Release | Required |  |  |  |  | WORLEYPARSONS-BRENTFORD, MIDDLESEX, UNITED KINGDOM |  |  |  |  | Windows XP |  | 0 | Open |  | 1 |  |  | ==== State: Investigated by: Pradeep_Polisetty on 31 January 2014 14:59:24 ==== I mistakenly said that there was an issue with Typical Installation but not it is with Custom Installation. In V8.4 there was also an Advance Intsall option which installs everything and I believe in V8.6 we are completely removing the Custom Install. So I think this issue is no longer applicable and we can close this issue. Thanks, Pradeep ==== State: Approved by: Pradeep_Polisetty on 24 October 2013 09:25:23 ==== Hi Gopal, Thanks for your response. I see now why the customer is having issues. Good that you have recommended him to use Typical Installation. Please let us know after you hear back. We still need to address this issue with Typical Installation so I will leave this CQ open until we resolve that. Thanks, Pradeep ==== State: Approved by: Gopal_Paul on 24 October 2013 06:11:15 ==== Pradeep, I did not receive any update from the customer. I was away delivering training. I called him today. He confirmed me that the IT people did a custom installation. I recommended him to ask their IT people for a typical installation. I will update you when they confirm the outcome after the typical installation. Gopal ==== State: Approved by: Pradeep_Polisetty on 18 October 2013 14:17:30 ==== Gopal, Did you receive any update from the customer? ==== State: Approved by: Pradeep_Polisetty on 15 October 2013 16:10:52 ==== Hi Gopal, Have you heard back from the customer? Last Friday you sent an email to me saying that Customer had issues installing HYSYS V8.3. Has that issue been resolved? In an attempt to reproduce customer's issue, I first installed Aspen HYSYS V8.2 and Aspen Plus V8.2 on XP machine. Then installed V8.3 versions for both products and finally ran aspenONE batch update file to install all available V8.3 updates for all products. I still couldn't reproduce customer's issue and I was able to setup Acid Gas Fluid Package properly and was able to enter into HYSYS Simulation Environment. Just thought would let you know. I am not sure how we should take this forward and it is very critical to get Amrut up and running with HYSYS V8.3 so that other engineers in his company can also start using HYSYS V8.3 Pradeep ==== State: Approved by: Pradeep_Polisetty on 15 October 2013 12:43:51 ==== We (R&D) are still not able to reproduce this issue that Customer is facing with installing/using Acid Gas functionality on a XP machine. Hence approving this defect with "Stand-by" as the Target release. We are working with the Customer to identify the problem. ==== State: Assigned by: Gopal_Paul on 10 October 2013 10:21:08 ==== Pradeep, Just finished a webex meeting with the customer. - The customer only installed HYSYS & Flarenet from V8.3 on his XP PC - Running "aspenONE Patch Update.exe" only updated paches for this two products - I send the acidgas.ilb to the customer but this did not help - I asked two installed two patches manually those are AspenPropertiesV8.2_Patch1.exe and ProcessModeling(AspenPlus)V8.2_Patch1.exe but was not installed returned with -1. If you want the error messages I can add those in this CQ. Could you test installing only HYSYS on a XP PC. Gopal ==== State: Assigned by: Pradeep_Polisetty on 10 October 2013 10:10:13 ==== Gopal, Is there any update from the customer on this issue? Pradeep ==== State: Assigned by: Pradeep_Polisetty on 09 October 2013 10:45:19 ==== Gopal, I just looked at V8.3 DVD contents and there is a file at the root level that should be named as "Read Me First ¿ Upgrade Guide for aspenONE V8.3.pdf" and on page 2, Item 4 clearly mentions that you need to apply all the latest patches by going to the folder \Engineering\Patches\ and then by running update agent "aspenONE Patch Update.exe" Pradeep ==== State: Assigned by: Pradeep_Polisetty on 09 October 2013 10:23:19 ==== Gopal, The updates were released along with V8.3 release and not after the release. This would be mentioned somewhere in release notes and I am not sure where that would be but it is definitely mentioned that one has to run "aspenONE Update Center" to get all updates. I installed these updates by going to Support Website, then clicked Patches on the left hand side and then ran "aspenONE Update Center" from the available option and that shows you all available updates and I would recommend to install all of them. I am not sure if I understand "Ram memory question" ... Other way to check that if things got installed correctly would be by going to "C:\Program Files\AspenTech\APrSystem V8.2\Engine\Xeq" and check the size of "acidgas.ilb" file and if the size is about 533 KB them updates are not installed. The correct size of this file should be 857 KB. Hope that helps but I am not sure if we usually instruct customers to check the install in this way. Pradeep ==== State: Assigned by: Gopal_Paul on 09 October 2013 10:05:29 ==== Hi Pradeep, Thank you for testing this. Now the problem is how to proceed with the customer problem. I did not find any update after the release of V8.3. There is no information in the support site about update of V8.3 that I can provide the customer to convince this. I can ask the Ram memory question to the customer to find out if this too small. Thanks, Gopal ==== State: Assigned by: Pradeep_Polisetty on 09 October 2013 09:54:29 ==== Hi Gopal, I had installed V8.3 on a Win XP VM and was able to successully run the new Acid Gas functionality released in HYSYS V8.3. I was able to do the following three steps successfully: 1. On the XP machine using HYSYS V8.3, created a new case and then I was able to create an Acid Gas Fluid Package with MDEA, H2S, CO2, and H2O and was able to enter Simulation Environment and this confirm that the Acid Gas Package setup step is successful. 2. On the XP machine using HYSYS V8.3, successfully loaded an Acid Gas example case that is develivered, then entered into Properties Environment and was able to edit the component list by adding a new component. I was able to successfully enter into Sim Env and solved the entire flowsheet without any issues. The columns in this sample case were using the default "Efficiency" method for Calculation Type. 3. With HYSYS V8.3, I was also able to create a Aspen Properties Fluid Package with an Aspen Properties component list and Electrolyte_NRTL as the Aspen Property method and was able to to enter Simulation Environment to confirm that the Aspen Properties setup step is successful. However, inorder to run the columns using "Advanced Modeling" for Calculation Mode on an Win XP machine, one would need to enable 3GB option to run Acid Gas Columns in "Advanced Modeling" mode otherwise Aspen HYSYS will crash. From above steps, its clear that Acid Gas functionality should work on a XP machine. In my earlier communication, I mentioned about patches. What I meant was to make sure that Customer had run "aspenONE Update Center" from Customer Support Website and this will bring few additional updates that were released with August release and these updates are critical for Acid Gas functionality to correctly work. Please find out from the customer if they had performed this step. Thanks, Pradeep ==== State: Assigned by: Gopal_Paul on 09 October 2013 08:11:04 ==== Hi Pradeep, I spoke to the system guy who helped to install V8.3 for WorelyParsons. He confirmed me that the typical (recommended) option was selected. I had a webex meeting, we were able to add aspen properties components and aspen properties electrolyte NRTL package without any problem. As far as I know there is no patch update available for V8.3. Thanks, Pradeep ==== State: Assigned by: Pradeep_Polisetty on 08 October 2013 15:58:01 ==== Hi Gopal, We did test Acid Gas functionality on Win XP during V8.3 release cycle. I am also in the process of setting up V8.3 on a XP machine and will update you once I finish the setup and do some tests. Meanwhile, can you please let us know what option the customer had selected when installing V8.3, Custom or Typical (recommended)? There are some know issues when one selects Custom installation option and pick Aspen HYSYS and Aspen Properties and when one does this I believe there are some issues using Aspen properties in HYSYS but from your below notes, Customer is able to create and use an Aspen Properites FP and component list in HYSYS V8.3; Please find out what option the customer had used while installating V8.3. Also, can you please find out if the customer had installed all the patches (run Update Center) required for V8.3? Thanks, Pradeep | 0 | 0 | Withdrawn | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open | N/A | ==== State: Submitted by: Scopus_Incident on 08 October 2013 05:02:54 ==== Defect created by Support from Incident: 1341586 By: Gopal_Paul Customer: WorleyParsons at Site: WORLEYPARSONS-BRENTFORD, MIDDLESEX, UNITED KINGDOM Customer Contact: Sharma, Amrut at +44 208 326 5000 Incidents Date and Time Stamps: Created: 07-Oct-2013 06:45 SLA: 16-Oct-2013 06:45 Client: 16-Oct-2013 06:45 Incidents Area Word(s): Sample Applications - Steady State,Acid Gas Cleaning ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1341586 ======================================================= ID: 3871729Filename: 2013_October_07_8500715.msg Size: 60928 ID: 3871832Filename: image001.jpg Size: 1943 ID: 3871833Filename: 2013_October_07_8500776.msg Size: 52736 ID: 3871840Filename: image001.jpg Size: 1943 ID: 3871841Filename: 2013_October_07_8500781.msg Size: 72192 ID: 3871886Filename: RegHYSYS_V83xp.txt Size: 1432 ID: 3871887Filename: 2013_October_07_8500814.msg Size: 40960 ID: 3871917Filename: image001.png Size: 135882 ID: 3871918Filename: 2013_October_07_8500840.msg Size: 192000 ID: 3872007Filename: image001.png Size: 10121 ID: 3872008Filename: 2013_October_07_8500899.msg Size: 50176 ID: 3872823Filename: image001.png Size: 10121 ID: 3872824Filename: 2013_October_07_8501478.msg Size: 69120 ID: 3886787Filename: 2013_October_08_8514808.msg Size: 32768 ID: 3887627Filename: 2013_October_08_8515632.msg Size: 51200 ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: WorleyParsons Site: WORLEYPARSONS-BRENTFORD, MIDDLESEX, UNITED KINGDOM Caller: Sharma, Amrut Incident Product: Aspen HYSYS Creation Date: 08-Oct-2013 04:54AM Applicable Version(s): --------------------------------- V8.3 Problem Description: --------------------------------- Acid Gas package does not work on customer PC. The issue is possibly related with Windows XP. Did the QE tested this on a XP PC? I had a webex meeting with the customer and tested the following: - Only few components added and Acid Gas package selected: Unable to enter the simulation. The trace windows shows: Failure Initializing Problem Definition. - The user was able to open an example case. But any modification (such remove n-pentane) in the component list caused the same failure. I have tested that the aspen properties is not a problem. The only difference is that Woleryparsons is still using the XP. I would suugest QE to test this on a XP PC. Steps to Reproduce: -------------------------------- Development Required Action: ------------------------------------------------
CQ00523942 | aspenONE uninstall failure | 2013-10-16 16:52 | Aspen Engineering Suite | AES Install | Uninstall |  | AspenTech Sandbox | 2-Critical | 1-Critical | S1-Critical | Closed | In Progress | No Activity | V8.3 |  | Michael.Yu@aspentech.com | Yu, Michael (Zhaoxiang) | simon.lingard@aspentech.com | V8.3 | n/a | 0 | Crash/Freeze | Customer |  | Required |  |  |  |  | Conoco Phillips | 8 | [5 empty] | 0 | Open |  |  | Michael.Yu@aspentech.com | Yu, Michael (Zhaoxiang) | ==== State: Closed by: ZiJuan_Wang on 29 April 2014 03:05:44 ==== Customer issue has been resolved, and both QE & DEV team cannot reproduce the issue. So no code fix needed. Now closing the defect ==== State: PendingVerification by: Tracy_Wang_Yuqing on 25 October 2013 01:51:20 ==== Please find notes below, Sudhir said this issue has been solved for customer. ==== State: Approved by: Tracy_Wang_Yuqing on 25 October 2013 01:49:32 ==== From: Chepeni, Sudhir Sent: 2013¿10¿25¿ 1:58 To: Yu, Michael (Zhaoxiang); Lingard, Simon; Yeung, Jeremy; Lonappan, Sajan Kallely Cc: Mohan, Sandeep; Campbell, Edward; Wang, Tracy (Yuqing) Subject: RE: Critical Customer Install Issue Thanks for follow up. I was working with customer and did not want to give bad experience so I requested the server reset and went ahead doing a clean install. Yes the problem is solved for customer. Thanks Sudhir From: Yu, Michael (Zhaoxiang) Sent: Wednesday, October 23, 2013 10:35 PM To: Lingard, Simon; Yeung, Jeremy; Chepeni, Sudhir; Lonappan, Sajan Kallely Cc: Mohan, Sandeep; Campbell, Edward; Wang, Tracy (Yuqing) Subject: RE: Critical Customer Install Issue Hi Sudhir, Is this issue solved in customer side? If not, I think we can try below two method to solve the uninstall issue. 1. Attached file is AspenAboutBox.dll, please manually copy file to ¿C:\Program files\Common Files\AspenTech Shared¿ folder (please overwrite the file if it existed in folder), then register the file with comman ¿Regsvr32.exe AspenAboutBox.dll¿. After this please do uninstall again. I think the issue should be solved. 2. Please do a repair install and uninstall product again. The issue should be solved. Could you please let me know what happened if the issue still exised? Thanks in advance. Best Regards, ==== State: Approved by: Tracy_Wang_Yuqing on 18 October 2013 05:44:35 ==== Michael, although you cannot reproduce the issue, we need help customer to proceed uninstall successfully. Please send the aspenaboutbox.dll and relevant aboutbox files to Simon, and tell them copy to which place. Simon, can you help pass the files to customer? ==== State: Submitted by: Michael_Yu on 17 October 2013 05:17:23 ==== I tested Platinum and aspenONE on 2008 server r2, during installation and uninstallation, there is no error reported. All tests are pass. ==== State: Submitted by: Michael_Yu on 17 October 2013 04:31:26 ==== I did not see this error in V8.4. Before I release each V8.4 media, on my test machine I will uninstall the last build first and then reinstall the new build. I have done this test many time and did not see this error. ==== State: Submitted by: Tracy_Wang_Yuqing on 17 October 2013 04:21:21 ==== Do you see this error in V8.4? Customer reported it in v8.3 |  | 0 | Fixed | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open |  | ==== State: Submitted by: Simon_Lingard on 16 October 2013 17:37:30 ==== The attached error occurs when uninstalling aspenONE. After this message, customer restarted the system, and tried to uninstall again and received the same message. In addition, aspenONE checkbox is grayed out, so we need to cleanly uninstall before we can reinstall. From the attached error message, looks like an error while unregistering a common component (AspenAboutBox.dll), not specific to aspenONE (Web). I¿m guessing that the component won¿t uninstall because it is in use? Perhaps the AspenAboutBox dialog is open ¿ how do we check? How can customer cleanly uninstall after receiving this message?
CQ00524040 | W&D Alpha: User shouble be able to cancel out from a deviation | 2013-10-17 15:27 | Batch Management | Aspen Production Execution Manager | Weigh and Dispense | Deviation | AspenTech Sandbox | 3-High | 2-Urgent | S2-Major | Closed | In Progress | No Activity | V8.7 |  | Wilson.Gong@aspentech.com | Eric Zhao | birch.chen@aspentech.com | V8.6 | MEDIA34A | 0 | Does Not Work As Designed | Customer | Beta Testing | Completed | Dicson.Leung@aspentech.com | Dicson Leung | 2013-10-21 10:47 |  | GlaxoSmithKline | 2 | [5 empty] | 0 | Open | 0 | 8 | Wilson.Gong@aspentech.com | Eric Zhao | ==== State: Closed by: Lily_Chi on 14 January 2014 00:39:54 ==== Cancel button is added. close it ==== State: Implemented by: Wilson_Gong on 14 November 2013 02:35:52 ==== This CQ is cause by Cancel button was not design to deviation screen Update CreateDeviationPanel, add cancel button and handler Reproducible : Yes Time to fix : 1 hours Risk: none Doc impact : none Recommend : Approve in V8.6 ==== State: Investigated by: Xiaoyong_Yu on 18 October 2013 11:53:44 ==== It looks reasonable to allow user go back and correct the problem before any deviation is created unless the use case require an automatic deviation created. |  | 0 | Fixed | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open |  | ==== State: Submitted by: Birch_Chen on 17 October 2013 16:05:13 ==== For example, if operator accepts weight when the weight is out-of-range (weight bar in yellow or red), user cannot cancel out and go back to adjust the dispensed quantity. User should be able to cancel out from a deviation screen and go back to take actions to avoid the deviation.
CQ00524653 | Will AFO V8.4 support Windows 8? | 2013-10-24 05:48 | Aspen Retail Family | Aspen Retail | Overall Application | WTS Support | AspenTech Sandbox | 5-Low | 3-Important | S3-Medium | Closed | In Progress | No Activity | V8.4 |  | reed.snellenberger@aspentech.com | Eric Zhao | CheeHoe.Sam@aspentech.com | V8.4 |  | 0 | Question | Customer | Requirements | Completed | Ike.Okogwu@aspentech.com | Okogwu, Ike | 2013-10-24 11:58 |  | SINOPEC-BEIJING, CHINA | 1 | [5 empty] | 0 | Open | 0 | 4 | reed.snellenberger@aspentech.com | Eric Zhao | ==== State: Closed by: Ike_Okogwu on 24 October 2013 11:58:32 ==== Answered. ==== State: Implemented by: Reed_Snellenberger on 24 October 2013 11:30:19 ==== Changed defect type to Question, "Found in" to Requirements. AFO V8.4 will be supported on both Windows 8 and Windows Server 2012. However, I don't know if this information can be released to customers prior to the official V8.4 announcement. |  | 0 | Answered | Description of resolution: See notes |  | None |  |  | Open |  | ==== State: Submitted by: CheeHoe_Sam on 24 October 2013 05:51:47 ==== http://cst.corp.aspentech.com/internalcgi/Incidentdisplay.cgi?key=1345852 Problem description: SINOPEC attempted to install 2006.5 AFO on Windows 8 platform. I've replied to them that AFO 2006.5 is not supported on Windows 8. I have also encouraged them to upgrade to V8. However, they have a concern with Windows 8 support. Please advise when and if Windows 8 will be supported by AFO V8.x and which release. ENG V8.2 products have started Windows 8 support. Steps to reproduce: Expected results: Development action required: Please advise when and if Windows 8 will be supported by AFO V8.x and which release.
CQ00525077 | MBO version 8.4.20 bug, screen bleed through when trend chart divider moved to left | 2013-10-29 10:36 | Aspen PIMS Family | Aspen Refinery Multi-Blend Optimizer | Event Operation |  | AspenTech Sandbox | 4-Medium | 4-Minor | S4-Minor | Closed | In Progress | No Activity | V8.4 |  | Boris.Zamsky@aspentech.com | Eric Zhao | Osiris.Fernandez@aspentech.com | V8.8 | 12.9.0 | 0 | Cosmetic | Customer | Post Release | Completed | Donna.Fontenot@aspentech.com | Fontenot, Donna | 2013-10-30 11:44 |  | EXXONMOBIL-FAIRFAX, VA | 8 |  |  |  | Multiple - See Configuration |  | 0 | Open |  | 16 | Boris.Zamsky@aspentech.com | Eric Zhao | ==== State: Closed by: Donna_Fontenot on 11 March 2015 16:11:57 ==== This defect was verified and closed by Donna Fontenot. Please see attached verification document. ==== State: PendingVerification by: Purvi_Bharwada on 05 September 2014 18:25:40 ==== Pending Verification ==== State: Implemented by: Boris_Zamsky on 28 July 2014 18:03:30 ==== Improved some redrawings ==== State: Approved by: Stacy_Janak on 24 July 2014 11:47:39 ==== Related to CQ00545394. Reapproved for V8.9. ==== State: PendingVerification by: Shuanglai_Zhang on 23 July 2014 01:43:48 ==== Tested on MBO V8.7 Build B083/7.7.39.0 32 bit installation on Windows 8.1 64-bit System The defect is still reproducible. Please refer to the attached screenshot. Steps: 1¿Open Demo access model in MBO. The Gasoline Blending event screen opens by default. 2. Optimize the model. After optimization, the HTML report opens. 3. Select the Gasoline Blending screen again. 4. Increase the size of the trend section by moving the divider left. Now you can see the issue. ==== State: Submitted by: Osiris_Fernandez on 29 October 2013 10:38:27 ==== Forgot to say you can use demo model to reproduce |  | 0 | Fixed | Improved some redrawings | Unintended Side-Effect | Coding | It was actually a problem of MFC. I found a work around. |  | Open | N/A | ==== State: Submitted by: Scopus_Incident on 29 October 2013 10:35:35 ==== Defect created by Support from Incident: 1347253 By: Osiris_Fernandez Customer: ExxonMobil at Site: EXXONMOBIL-FAIRFAX, VA Customer Contact: Evans, Joe at 1-703-846-5326 Incidents Date and Time Stamps: Created: 29-Oct-2013 08:37 SLA: 02-Dec-2013 09:00 Client: 02-Dec-2013 09:00 Incidents Area Word(s): Area words were blank ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1347253 ======================================================= ID: 4012518Filename: Screen bleed through.PNG Size: 76140 ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Creation Date: 29-Oct-2013 10:33AM Applicable Version(s): --------------------------------- MBO v8.4 Problem Description: --------------------------------- Please see the example of this effect in the attached screen shot. Annoying, but not what I would expect from a quality application. Steps to Reproduce: -------------------------------- Support comments: Reproduced in v8.4. Try it out opening two tabs in Ecevt interface, such as : Gasoline blending and Validation log or HTML optimization report. Then move trand chart divider (small trends) to the left. Development Required Action: ------------------------------------------------ QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: ExxonMobil Site: EXXONMOBIL-FAIRFAX, VA Caller: Evans, Joe Incident Product: Aspen Refinery Multi-Blend Optimizer
CQ00525091 | Large controller crashes on Foxboro due to slow I/O | 2013-10-29 12:41 | Advanced Control Family | Aspen DMCplus | DMCplus Cim-IO | Interface | AspenTech Sandbox | 2-Critical | 3-Important | S3-Medium | Closed | In Progress | No Activity | V8.4 |  | subhash.ghorpade@aspentech.com | Ghorpade, Subhash | Andy.Patrachari@aspentech.com | V8.4 | RC8 | 0 | Does Not Work As Designed | Customer | Beta Testing | Completed | Randy.Burch@aspentech.com | Randy Burch | 2015-09-14 17:48 |  | BAYERNOIL RAFFINERIE GMBH-NEUSTADT, GERMANY | 4 |  |  |  | Windows 2008 Server |  | 0 | Open | 0 |  | subhash.ghorpade@aspentech.com | Ghorpade, Subhash | ==== State: Closed by: Jesus_Martinez on 23 April 2015 17:46:50 ==== From: Clark, Christopher Sent: Thursday, April 23, 2015 1:05 PM To: Hensley, Bill; Elliott, Jon; Burch, Randy Cc: Martinez, Jesus Subject: RE: Question about V7.3 CP5 and V8.0 CP3 Yes. Those fixes are included in those patches. ==== State: Closed by: Jesus_Martinez on 23 April 2015 10:42:29 ==== CQ00487215, CQ00504469, CQ00514738, CQ00518489 & CQ00525091 associated to NonLinear controller are fixed in V7.3 CP4 EP2 and V8.0 CP2 EP5. The V7.3 CP5 and V8.0 CP3 include them? Their Release Notes don¿t mention those CQ¿s. ==== State: Closed by: Randy_Burch on 12 November 2013 14:28:40 ==== Although this issue was noted by the customer for specific use of Cim-IO Foxboro API interface, it is not reproducible through in-house testing for the same large DMCplus control application using InfoPlus.21 database tags and Cim-IO IP.21 interface. Closing this issue based on code review for applied changes and customer validation for resolving the previous problem after applying a Hot Fix. The implemented Hot Fix changes are included in the v84r1 source tree. dmcp_dataengine.dll, dmcp_datapump.exe version 14.0.1.1007 ==== State: Approved by: Bill_Hensley on 31 October 2013 21:05:38 ==== I'm changing the headline to be more descriptive. It was "Aspen Adaptive Modeling V8.4 Beta Testing." |  | 0 | Fixed | Description of resolution: Removed recursive lock exception. Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: dmcp_dataengine.dll Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open | No | ==== State: Submitted by: Scopus_Incident on 29 October 2013 12:41:11 ==== Defect created by Support from Incident: 1346956 By: Andy_Patrachari Customer: BayernOil at Site: BAYERNOIL RAFFINERIE GMBH-NEUSTADT, GERMANY Customer Contact: Stricker, Martin at 084572115 Incidents Date and Time Stamps: Created: 28-Oct-2013 10:21 SLA: 06-Nov-2013 10:21 Client: 06-Nov-2013 10:21 Incidents Area Word(s): Multi-Product Integration ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Attachments associated with the Scopus Incident can be found at \\csfiles.hou.aspentech.com\files\incidents\1346956 ======================================================= ID: 4009707Filename: Event Messages.txt Size: 3612 ID: 4010178Filename: 2013_October_28_8619488.msg Size: 52736 ID: 4010200Filename: 2013_October_28_8619502.msg Size: 55808 ID: 4010252Filename: 2013_October_28_8619545.msg Size: 58880 ID: 4010358Filename: 2013_October_28_8619627.msg Size: 61440 ID: 4010929Filename: BO_dmcp_dataengine.zip Size: 85842 ID: 4010930Filename: 2013_October_28_8620026.msg Size: 274432 ID: 4014933Filename: 2013_October_29_8622689.msg Size: 103424 ++++++++++++++++++++++++++++++++++++++++++++++++++++++++ Creation Date: 28-Oct-2013 01:22PM Applicable Version(s): --------------------------------- v8.4 Problem Description: --------------------------------- From Client- We have a big issues with the beta version 8.4 you gave Eric Janssen and us for testing. We need to start SmartStep/Calibrate now for our project at BayernOil but arent be able to change values on the PCWS. Everytime we try this, the dmcp_ddatapump service crashes and all apps of the server hang up. I took a deeper look into windows events, the corresponding error-events are attached to the email. After WebEx, from Subhash- I just concluded the webex call with Martin Stricker and we have successfully resolved the problem. The customer has a large controller (50 MV X 100s of CV) with many tags connected to Foxboro DCS. Sometimes the DCS Write to Foxboro takes longer than a minute. The request to change entry value from DMCplus Data Service to the dmcp_dataworker.exe has a default timeout of 1 minute and would get a timeout exception when the DCS IO took a long time. We have a retry logic that would increase the timeout by 30 seconds and retry up to 6 times. However, there was a bug in this code that caused a recursive lock exception and crashed the DMCplus data service. I sent him the attached hotfix DLL that fixed the retry logic. Steps to Reproduce: -------------------------------- N/A Development Required Action: ------------------------------------------------ Include fix in v8.4 CP1 QCI Created from an Incident (First Customer Information is) ---------------------------------------------------------------------------------------- Company: BayernOil Site: BAYERNOIL RAFFINERIE GMBH-NEUSTADT, GERMANY Caller: Stricker, Martin Incident Product: Aspen Adaptive Modeling
CQ00526764 | An assay branch should not be required to have any Pure Component streams | 2013-11-14 14:23 | Aspen PIMS Family | Assay Manager | Overall Application | General | AspenTech Sandbox | 3-High | 2-Urgent | S2-Major | Closed | In Progress | No Activity | V8.4 | 2.4.0.34 | Zongning.Ma@aspentech.com | Ma, Zongning | Mel.Bernstein@aspentech.com | V8.5 | 24 | 0 | Functionality Loss | Customer | Implementation | Required |  |  |  |  | PTT | 3 |  | Windows 8 - 64bit |  |  |  | 0 | Open |  |  | Zongning.Ma@aspentech.com | Ma, Zongning | ==== State: Closed by: Ying_Li on 01 December 2013 21:20:45 ==== Verified on V8.5 B25a, OS: Win8-64bit, Office2013. 1. Open PIMS with attached model, and launch Assay manager. 2. Click setup wizard, select assays from PIMS, and give IBP and FBP for some cuts, others set as non-distillation under Define cut point. 3. Transfer assays, it can be completed successfully. 4. Characterize some assays, check cut crude window. There is no Pure Component tab, only update the assays characterized, click generate results, the results can be shown. See attachment. ==== State: Implemented by: Zongning_Ma on 20 November 2013 20:53:03 ==== Hi Suphat, Thanks. Zongning ==== State: Implemented by: Suphat_Watanasiri on 20 November 2013 07:57:45 ==== Zongning, Thanks. I am attaching the PIMS model file from PTT provided by Mel to be used in verifying the defect. Suphat ==== State: Implemented by: Zongning_Ma on 20 November 2013 03:19:17 ==== Fixed. Thanks, Zongning ==== State: Approved by: Zongning_Ma on 19 November 2013 04:21:40 ==== Hi Mel, I fixed this issue after talking with Shu. Could you please give me the PPT's model to do testing? Thanks, Zongning |  | 0 | Fixed | Description of resolution: Description of workaround (if applicable): Source Files Changed: Deliverable Files Affected: Tests performed and/or recommended to be performed: Documentation resolution description: |  | None |  |  | Open | Poor | ==== State: Submitted by: Mel_Bernstein on 14 November 2013 14:28:46 ==== In PTT's model, one of the assay branches modelled a distillation column that we fed by a reduced crude - that is the light components had been removed. The lightest cut had an IBM of about 100 DegF. There were no "Pure Component" streams defined. This caused 2 problems. First, when I tried to import a crude from that assay table, it wouldn't do it. Second, when I got to the Cut Crudes, both the Setup and Pure Component tabs showed errors that could not be remedied. There is no requirement for any light end or pure component streams in PIMS, and there should not be in AAM.